## RF
S.N. | TaskCategory | Region | Site/Location | ParentSite | Address | Lat | Lon | TaskType | Task Description | Band | TaskStatus | Transmission | Scope | Date | Remarks/Recomendation | GOAL
1 | Network Coverage Expansion | WDR-BUT | WDR474_Sunawal | WDR474_Sunawal | Sunawal |  |  | High Gain Antenna | 1 Sector | 2G 900MHz | Installed |  | NT
2 | Network Coverage Expansion | WDR-BUT | WDR013_Jaluke | WDR013_Jaluke | Arghakhachi |  |  | High Gain Antenna | 1 Sector | 2G 900MHz | Installed |  | NT
3 | Network Coverage Expansion | WDR-BUT | WDR423-Daunnedevi | WDR423-Daunnedevi | Nawalparasi |  |  | High Gain Antenna | 1 Sector | 900MHz | Installed |  | NT
4 | Network Coverage Expansion | CDR-SUN | CDR465_RAMCHE | CDR465_RAMCHE | Ramche Rasuwa |  |  | High Gain Antenna | 1 sector | 900 MHZ | Installed |  | NT
5 | Network Coverage Expansion | CDR-TTC | CDR123_Gajuri | CDR123_Gajuri | Dhading |  |  | High Gain Antenna | 1 Sector | 3G | Installed |  | NT
6 | Network Coverage Expansion | CDR-TTC | Naagdhunga Tunnel | New Site Plan | Dhading |  |  | High Gain Antenna | 2 Sector | 2G | Planned |  | NT
7 | Network Coverage Expansion | WDR-BUT | WDR423-Daunnedevi | WDR423-Daunnedevi | Daunne |  |  | High Gain Antenna | 1 Sector |  | Installed |  | NT
8 | Network Coverage Expansion | CDR-TTC | Naagdhunga Tunnel | New Site Plan | Dhading, Kathmandu |  |  | High Gain Antenna | 1 Sector |  | Planned |  | NT
9 | Network Quality Improvement | CDR-HTD | CDR099_Ramnagar | CDR099_Ramnagar | Chitwan |  |  | High Gain Antenna | 1 Sector |  | Planned |  | NT
10 | Network Quality Improvement | CDR-TTC | Sanjen Hydro |  | Rasuwa |  |  | Repeater |  |  | Installed |  | NT
11 | Network Quality Improvement | KTM | World Bank Group |  | Lazimpat |  |  | Repeater |  |  | Installed |  | NT
12 | Network Quality Improvement | KTM | World Bank Group |  | Durbarmarg |  |  | Repeater |  |  | Installed |  | NT
13 | Network Quality Improvement | WDR-POK | Ghiring Rural Municipality |  | Tanahu |  |  | Repeater |  |  | Installed |  | NT
14 | Network Quality Improvement | KTM | Mahotsav Restaurant |  | Laldurbar Kathmandu |  |  | Repeater |  |  | Installed |  | NT
15 | Network Quality Improvement | CDR-TTC | Trishuli 3A Office |  | Nuwakot |  |  | Repeater |  |  | Planned |  | NT
16 | Network Quality Improvement | KTM | Infinity Mall |  | Gongabu |  |  | Repeater |  |  | Planned |  | NT
17 | Network Quality Improvement | KTM | Police Hospital |  | Lazimpat |  |  | Repeater |  |  | Planned |  | CCSI
18 | Network Quality Improvement | KTM | Eagle Logistic |  | Chhetrapati |  |  | Repeater |  |  | Planned |  | NT
19 | Network Quality Improvement | KTM | Himalayan Bank |  | Bishalbazar |  |  | Repeater |  |  | Planned |  | NT
20 | Network Quality Improvement | WDR-POK | Dulegauda Nagarpalika |  | Dulegauda |  |  | Repeater |  |  | Planned |  | NT
21 | Network Quality Improvement | KTM | Tandoori Fast Food Café |  | Newroad |  |  | Repeater |  | 2G/3G | Installed |  | NT
22 | Network Quality Improvement | KTM | GBIME |  | Kamaladi |  |  | Repeater |  | 2G/3G | Installed |  | NT
23 | Network Quality Improvement | KTM | Park Village Resort |  | Budhanilkantha |  |  | Repeater |  | 2G/3G | Installed |  | NT
24 | Network Quality Improvement | KTM | Square Hotel |  | Pulchwok, Lalitpur |  |  | Repeater |  | 2G/3G | Installed |  | NT
25 | Network Quality Improvement | KTM | Radission Hotel |  | Lazimpat |  |  | Repeater |  | 2G/3G | Installed |  | NT
26 | Network Quality Improvement | KTM | Standard Chartered Bank |  | Baneswore, Kathmandu |  |  | Repeater |  | 2G/3G | Planned |  | NT
27 | Network Quality Improvement | CDR-TTC | Madhya Bhotekoshi |  | Sindhupalchwok |  |  | Repeater |  | 2G/3G | Planned |  | NT
28 | Network Quality Improvement | CDR-TTC | Department of Road |  | Babarmahal Kathmandu |  |  | Repeater |  | 2G/3G | Planned |  | NT
29 | Others | KTM | Samanya Prasasan Mantralaya |  | Singhdurbar |  |  | Repeater Dismantled |  |  | Dismantled | - | NT
30 | Others | KTM | Bidhan Bista |  | Jhamsikhel |  |  | Repeater Dismantled |  |  | Dismantled | - | NT
31 | Others | KTM | Green Law Firm (Action) |  | Putalisadak |  |  | Repeater Dismantled |  |  | Dismantled | - | NT
32 | Others | KTM | Bindu Suwal |  | Choche, Bhaktapur |  |  | Repeater Dismantled |  |  | Dismantled | - | NT
33 | Network Coverage Expansion | MWDR | Jajarkot Rimna | MWDR098-NT jajarkot | Rimna |  |  | Sector Expansion | 1 Sector | 2G | Installed | Fiber | NT
34 | Network Coverage Expansion | KTM | Prime Minister Office | KTM289-Singhadurbar | Singhdurbar |  |  | Sector Expansion | 1 Sector | 3G | Installed | Fiber | NT
35 | Network Coverage Expansion | KTM | Godawari Conference Hall | KTM445-GodawariKunda | Godawari |  |  | Sector Expansion | 1 Sector | 3G | Installed | Fiber | NT
36 | Network Coverage Expansion | KTM | Switzerland Park | KTM146 | Indrasthan |  |  | Sector Expansion | 2 Sector | 2G/3G | Installed | Fiber | NT
37 | Network Coverage Expansion | CDR-TTC | Siddhalek 07, Pipaltar, Dhading | CDR123 | Gajuri |  |  | Sector Expansion | 2 Sector | 3G | Installed | Fiber | NT
38 | Network Coverage Expansion | KTM | Army Training Center | CDR625_Zerokilo | Paanch Khal |  |  | Sector Expansion | 2 Sector | 2G/3G | Installed | Fiber | NT
39 | Network Coverage Expansion | CDR-TTC | Alle Barrack | CDR102-Alle Barrack | Shivapuri National Park |  |  | Sector Expansion | 1 Sector | 2G/4G | Installed | Fiber | NT
40 | Network Coverage Expansion | KTM | Ranjana Trade Mall | KTM099_CrystalHotel | Bishal Bazar |  |  | Sector Expansion | 1 Sector | 3G | Installed | Fiber | NT
41 | Network Coverage Expansion | KTM | Radhe Radhe | KTM043 | Thimi |  |  | Sector Expansion | 1 Sector | 3G | Installed | Fiber | NT
42 | Network Coverage Expansion | KTM | Ullens School | KTM345_Dholahiti | Satdobato, Lalitpur |  |  | Sector Expansion | 1 Sector | 3G | Planned | Fiber | NT
43 | Network Coverage Expansion | KTM | CG Hotel And Resort | KTM383_SachalSanepa | Jhamsikhel |  |  | Sector Expansion | 1 Sector | 3G | Planned | Fiber | NT
44 | Network Coverage Expansion | CDR-TTC | Timure Bazar |  | Rasuwa |  |  | Sector Expansion | 2 Sector | 3G | Planned | Fiber | NT
45 | Network Coverage Expansion | MWDR | Guranse Nagarpalika |  | Dailekh |  |  | Sector Expansion | 1 Sector | 1800MHz | Planned | Fiber | NT
46 | Network Coverage Expansion | CDR-TTC | Panchkhal Army Camp | CDR625_Zerokilo | Kabhre |  |  | Sector Expansion | 2 Sector | 2G/3G | Installed | Fiber | NT
47 | Network Coverage Expansion | KTM | District Court Bhaktapur | KTM688-Chokha | Libali |  |  | Small Cell | 1 | 3G | Installed | Fiber | NT
48 | Network Coverage Expansion | KTM | Sankata Club | KTM742-Nepal Airlines | Tehbhal Sankata |  |  | Small Cell | 1 | 3G | Installed | Fiber | NT
49 | Network Coverage Expansion | KTM | Akash Galli | KTM299-NTSundhara | Sundhara |  |  | Small Cell | 1 | 3G | Installed | Fiber | NT
50 | Network Coverage Expansion | KTM | Army Training Center | CDR625_Zerokilo | Paanch Khal |  |  | Small Cell | 3 | 4G | Installed | Fiber | NT
51 | Network Coverage Expansion | KTM | Manmohan Cardiology | KTM200-Maharajgunj1 | Maharajgunj |  |  | Small Cell | 1 | 4G | Installed | Fiber | CCS
52 | Network Coverage Expansion | KTM | NIMB | KTM225-Narayanhitipalace | Lazimpat |  |  | Small Cell | 2 | 4G | Installed | Fiber | CCS
53 | Network Coverage Expansion | KTM | Green Law Firm | KTM174_Khasibazar | Putalisadak |  |  | Small Cell | 1 | 3G | Installed | Fiber | NT
54 | Network Coverage Expansion | KTM | Civil Hospital | KTM237_NewBaneshworChowk | Minbhawan |  |  | Small Cell | 1 | 3G | Installed | Fiber | NT
55 | Network Coverage Expansion | KTM | Santenswor Temple |  | Bajrabarahi, Lalitpur |  |  | Small Cell | 1 | 4G | Planned | Fiber | CCS
56 | Network Coverage Expansion | KTM | NAC |  | Sinamangal |  |  | Small Cell | 4 | 4G | Planned | Fiber | CCS
57 | Network Coverage Expansion | KTM | Mercur Hotle |  | Sukhedhara |  |  | Small Cell | 1 | 3G/4G | Planned | Fiber | NT
58 | Network Coverage Expansion | CDR-TTC | Siddhartha Hotel |  | Chumlingtar |  |  | Small Cell | 1 | 3G/4G | Planned | Fiber | NT
59 | Network Coverage Expansion | KTM | Hams Hospital |  | Mandikhatar |  |  | Small Cell | 2 | 4G | Planned | Fiber | NT
60 | Network Coverage Expansion | CDR-HTD | Hetauda Hospital |  | Hetauda |  |  | Small Cell | 1 | 4G | Planned | Fiber | NT
61 | Network Coverage Expansion | CDR-HTD | Churia Mai Temple |  | Hetauda |  |  | Small Cell | 1 | 4G | Planned | Fiber | NT
62 | Network Coverage Expansion | CDR-TTC | Furke Khola |  | Dhading |  |  | Small Cell | 1 | 3G/4G | Planned | Fiber | NT
63 | Network Coverage Expansion | KTM | Hilton Hotel |  | Naxal |  |  | Small Cell | 1 | 3G/4G | Planned | Fiber | NT
64 | Network Coverage Expansion | KTM | Kanti Children Hospital |  | Maharajgunj |  |  | Small Cell | 1 | 3G/4G | Planned | Fiber | NT
65 | Network Coverage Expansion | KTM | Nabil Bank |  | Sallaghari |  |  | Small Cell | 1 | 3G/4G | Planned | Fiber | NT
66 | Network Coverage Expansion | KTM | Royal Resort |  | Shivapuri National Park |  |  | Small Cell | 1 | 3G | Installed | Fiber | NT
67 | Network Coverage Expansion | KTM | Trade Tower |  | Maitighar |  |  | Small Cell |  | 3G/4G | Planned | Fiber | CCS
68 | Network Coverage Expansion | CDR-TTC | Panchkhal Army Camp |  | Kabhre |  |  | Small Cell | 2 Sector | 4G | Installed | Fiber | NT
69 | Network Coverage Expansion | KTM | Doleshwor Temple | KTM390-sipadole | Sipadol |  |  | Small Cell | 1 Sector | 3G | Installed | Fiber | NT
70 | Network Coverage Expansion | KTM | Sky Walk Wonder Nepal | KTM604 | Kamaladi |  |  | Small Cell | 1 Sector | 3G | Installed | Fiber | NT
71 | Network Coverage Expansion | KTM | Hotel Mount Fuji | KTM299-NTSundhara | Sundhara |  |  | Small Cell | 1 Sector | 3G | Installed | Fiber | NT
72 | Network Coverage Expansion | KTM | Tamrakar House | KTM099_CrystalHotel | Newroad |  |  | Small Cell | 1 Sector | 3G | Planned | Fiber | NT
73 | Network Quality Test | FWDR | Bhimdatta Mahendranagar |  | Bhimdatta |  |  | Drive Test | First Quarter | 2G 3G 4G | Completed |  | NT+ HW
74 | Network Quality Test | MWDR | Ghubhakot Municipality and Ramghat |  | Ghubhakot, Ramghat |  |  | Drive Test | First Quarter | 2G 3G 4G | Completed |  | NT+ HW
75 | Network Quality Test | FWDR | Kailari Ratnapur Area |  | Kailari |  |  | Drive Test | First Quarter | 2G 3G 4G | Completed |  | NT+ HW
76 | Network Quality Test | FWDR | Bajura |  | Bajure |  |  | Drive Test | First Quarter | 2G 3G 4G | Completed |  | NT+ HW
77 | Network Quality Test | MWDR | Kohalpur-Birendranagar Highway |  | Kohalpur-Birendranagar |  |  | Drive Test | First Quarter | 2G 3G 4G | Completed |  | NT+ HW
78 | Network Quality Test | WDR | Baglung |  | Baglung |  |  | Drive Test | Second Quarter | 2G 3G 4G | Completed |  | NT+ HW
79 | Network Quality Test | WDR | Pokhara-Butwal Highway |  | Pokhara-Butwal |  |  | Drive Test | Second Quarter | 2G 3G 4G | Completed |  | NT+ HW
80 | Network Quality Test | WDR | Bhairahawa Village |  | Bhairahawa |  |  | Drive Test | Second Quarter | 2G 3G 4G | Completed |  | NT+ HW
81 | Network Quality Test | MWDR | Rolpa |  | Rolpa |  |  | Drive Test | Second Quarter | 2G 3G 4G | Completed |  | NT+ HW
82 | Network Quality Test | MWDR | Pyuthan |  | Pyuthan |  |  | Drive Test | Second Quarter | 2G 3G 4G | Completed |  | NT+ HW
83 | Network Quality Test | MWDR | Rajpur-Keruhiya-Pirari-Bhaluwang |  | Rajpur-Keruhiya-Pirari-Bhaluwang |  |  | Drive Test | Second Quarter | 2G 3G 4G | Completed |  | NT+ HW
84 | Network Quality Test | WDR | Besisahar City |  | Besisahar City |  |  | Drive Test | Third Quarter | 2G 3G 4G | Completed |  | NT+HW
85 | Network Quality Test | KTM | KTM Valley DT |  | Kathmandu Bhaktapur Lalitpur |  |  | Drive Test | On Demand | 2G 3G 4G | Completed |  | NT+HW
86 | Network Quality Test | CDR | Bharatpur |  | Bharatpur City |  |  | Drive Test | On Demand | 2G 3G 4G | Completed |  | NT+HW
87 | Network Quality Test | WDR | Prithvi Highway |  | Major Highway |  |  | Drive Test | On Demand | 2G 3G 4G | Completed |  | NT+HW
88 | Network Quality Test | CDR | Mugling- Bharatpur Highway |  | Major Highway |  |  | Drive Test | On Demand | 2G 3G 4G | Completed |  | NT+HW
89 | Network Quality Test | CDR +EDR | Mahendra Highway (Bharatpur-Kakadvitta) |  | Major Highway |  |  | Drive Test | On Demand | 2G 3G 4G | Completed |  | NT+HW
90 | Network Quality Test | CDR+WDR | Kathmandu to Butwal Highway |  | Major Highway |  |  | Drive Test | Highway Coverage Test | 2G 3G 4G | Completed |  | NT
91 | Network Quality Test | KTM | Kathmandu Ringroad DT |  | City Roads |  |  | Drive Test | Ringroad Coverage Test | 2G 3G 4G | Completed |  | NT
92 | Network Expansion | KTM | Gongabu Ganesthan |  | Gongabu Ganeshthan |  |  | Site Survey | Site Survey | 2G 3G 4G | Completed |  | NT
93 | Network Expansion | KTM | Kirtipur Tyangla Phat |  | Kirtipur Tyangla Phat |  |  | Site Survey | Site Survey | 2G 3G 4G | Completed |  | NT
94 | Network Expansion | KTM | Shankarapur Wardno 4 |  | Shankarapur Municipalit |  |  | Site Survey | Site Survey | 2G 3G 4G | Completed |  | NT
95 | OSS Optimization | [6 empty] | RF Parameter Optimization | Implementation solution for 3G Daily maintenance and Cell parameter changes for Pkg A and B Network | 3G | Completed |  | HW | 2023-06-02
96 | OSS Optimization | [6 empty] | RF Parameter Optimization | Cell Optimization and RF Parameter Changes for NT WCDMA Network | 3G | Completed |  | HW | 2023-06-09
97 | OSS Optimization | [6 empty] | RF Parameter Optimization | GSM Cell Optimization and RF Parameter Changes for Networks of Package- A and B_Monthly-July 2023 | 2G | Completed |  | HW | 2023-06-12
98 | OSS Optimization | [6 empty] | RF Parameter Optimization | Implementation solution for 2G Daily Maintenance and Cell Parameter Changes for PKG A and B | 2G | Completed |  | HW | 2023-06-20
99 | OSS Optimization | [6 empty] | RF Parameter Optimization | Implementation solution for PS Call Drop Optimization in CDRHTD and CDRTTC UMTS Network | 3G | Completed |  | HW | 2023-06-22
100 | OSS Optimization | [6 empty] | RF Parameter Optimization | Implementation Solution for TRX Addition and GSM Congestion Optimization in PKG-A | 2G | Completed |  | HW | 2023-06-23
101 | OSS Optimization | [6 empty] | RF Parameter Optimization | 2G Cell Optimization and RF Parameter Changes for NTC Network Monthly | 2G | Completed |  | HW | 2023-06-28
102 | OSS Optimization | [6 empty] | RF Parameter Optimization | Implementation solution for 2G Daily Maintenance and Cell Parameter Changes for PKG A and B | 2G | Completed |  | HW | 2023-06-29
103 | OSS Optimization | [6 empty] | RF Parameter Optimization | Cell Optimization and RF Parameter Changes for WCDMA Networks of Package-A and B July _Monthly. |  | Completed |  | HW | 2023-07-06
104 | OSS Optimization | [6 empty] | RF Parameter Optimization | GSM Cell Optimization and RF Parameter Changes for Networks of Package- A and B_Monthly-August 2023 | 2G | Completed |  | HW | 2023-07-06
105 | OSS Optimization | [6 empty] | RF Parameter Optimization | Implementation solution for UL Power Congestion Optimization in Pkg A Network | 2G | Completed |  | HW | 2023-07-06
106 | OSS Optimization | [6 empty] | RF Parameter Optimization | Implementation solution for 3G Daily Maintenance and Cell Parameter Changes for PKG A and B. | 3G | Completed |  | HW | 2023-07-07
107 | OSS Optimization | [6 empty] | RF Parameter Optimization | Cell Optimization and RF Parameter Changes for NT WCDMA Network | 3G | Completed |  | HW | 2023-07-14
108 | OSS Optimization | [6 empty] | RF Parameter Optimization | 2G Cell Optimization and RF Parameter Changes for NTC Network Monthly | 2G | Completed |  | HW | 2023-07-26
109 | OSS Optimization | [6 empty] | RF Parameter Optimization | Implementation solution for 3G Daily Maintenance and Cell Parameter Changes for PKG A and B. | 3G | Completed |  | HW | 2023-07-27
110 | OSS Optimization | [6 empty] | RF Parameter Optimization | WCDMA Implementation solution for Daily Maintenance and Cell Parameter Changes- August | 3G | Completed |  | HW | 2023-08-01
111 | OSS Optimization | [6 empty] | RF Parameter Optimization | Implementation solution for 2G Daily Maintenance and Cell Parameter Changes for PKG A | 2G | Completed |  | HW | 2023-08-02
112 | OSS Optimization | [6 empty] | RF Parameter Optimization | GSM Cell Optimization and RF Parameter Changes for Networks of Package- A Monthly- 2023 |  | Completed |  | HW | 2023-08-03
113 | OSS Optimization | [6 empty] | Neighbor Audit | 2G Neighbor Audit FWDR ATRHBSC09 | 2G | Completed |  | HW | 2023-08-04
114 | OSS Optimization | [6 empty] | Neighbor Audit | 2G Neighbor Audit FWDR ATRHMBSC04 | 2G | Completed |  | HW | 2023-08-09
115 | OSS Optimization | [6 empty] | RF Parameter Optimization | Cell Optimization and RF Parameter Changes for PKG A WCDMA Network | 3G | Completed |  | HW | 2023-08-11
116 | OSS Optimization | [6 empty] | Neighbor Audit | 2G Neighbor Audit MWDR NPJHBSC10 | 2G | Completed |  | HW | 2023-08-11
117 | OSS Optimization | [6 empty] | RF Parameter Optimization | Implementation Solution for Voice Quality Index Feature Enable in TTCHMBSC02 | 2G | Completed |  | HW | 2023-08-11
118 | OSS Optimization | [6 empty] | Neighbor Audit | 2G Neighbor Audit MWDR NPJHMBSC05 | 2G | Completed |  | HW | 2023-08-15
119 | OSS Optimization | [6 empty] | Neighbor Audit | 2G Neighbor Audit for HTDHBSC07 | 2G | Completed |  | HW | 2023-08-18
120 | OSS Optimization | [6 empty] | Neighbor Audit | 2G Neighbor Audit CDR TTCHMBSC02 | 2G | Completed |  | HW | 2023-08-18
121 | OSS Optimization | [6 empty] | Neighbor Audit | 2G Neighbor Audit for HTDHBSC08 | 2G | Completed |  | HW | 2023-08-23
122 | OSS Optimization | [6 empty] | Neighbor Audit | 2G Neighbor Audit CDR HTDHMBSC03 | 2G | Completed |  | HW | 2023-08-23
123 | OSS Optimization | [6 empty] | RF Parameter Optimization | 2G Cell Optimization and RF Parameter Changes for NTC Network Monthly | 2G | Completed |  | HW | 2023-08-24
124 | OSS Optimization | [6 empty] | Neighbor Audit | 2G Neighbor Audit BRTHBSC11 | 2G | Completed |  | HW | 2023-08-29
125 | OSS Optimization | [6 empty] | RF Parameter Optimization | Implementation Solution for Voice Quality Index Feature Enable in HTDHBSC07 | 2G | Completed |  | HW | 2023-08-30
126 | OSS Optimization | [6 empty] | Neighbor Audit | 2G Neighbor Audit for BRTHMBSC06 | 2G | Completed |  | HW | 2023-08-30
127 | OSS Optimization | [6 empty] | RF Parameter Optimization | Implementation solution for 3G Daily Maintenance and Cell Parameter Changes for PKG A | 3G | Completed |  | HW | 2023-09-01
128 | OSS Optimization | [6 empty] | RF Parameter Optimization | GSM Cell Optimization and RF Parameter Changes for daily maintenance. | 2G | Completed |  | HW | 2023-09-08
129 | OSS Optimization | [6 empty] | Neighbor Audit | 3G Neighbor Audit for NPJHMBSC05 | 3G | Completed |  | HW | 2023-09-08
130 | OSS Optimization | [6 empty] | Neighbor Audit | 3G Neighbor Audit ATRHMBSC04 | 3G | Completed |  | HW | 2023-09-08
131 | OSS Optimization | [6 empty] | Feature Implementation | Implementation Solution for Voice Quality Index Feature Enable in HTDHMBSC03 | 2G | Completed |  | HW | 2023-09-08
132 | OSS Optimization | [6 empty] | Neighbor Audit | 3G Neighbor Audit BRTHMBSC06 | 3G | Completed |  | HW | 2023-09-12
133 | OSS Optimization | [6 empty] | Neighbor Audit | 3G Neighbor Audit TTCHMBSC02 | 3G | Completed |  | HW | 2023-09-12
134 | OSS Optimization | [6 empty] | Neighbor Audit | 3G Neighbor Audit HTDHMBSC03 | 3G | Completed |  | HW | 2023-09-14
135 | OSS Optimization | [6 empty] | RF Parameter Optimization | Cell Optimization and RF Parameter Changes for PKG A WCDMA Network | 3G | Completed |  | HW | 2023-09-15
136 | OSS Optimization | [6 empty] | RF Parameter Optimization | 2G Cell Optimization and RF Parameter Changes for NTC Network Monthly | 2G | Completed |  | HW | 2023-09-21
137 | OSS Optimization | [6 empty] | Feature Implementation | Implementation Solution for Voice Quality Index Feature Enable in NPJHBSC10 | 2G | Completed |  | HW | 2023-09-29
138 | OSS Optimization | [6 empty] | Feature Implementation | Implementation Solution for Voice Quality Index Feature Enable in ATRHBSC09 | 2G | Completed |  | HW | 2023-09-29
139 | OSS Optimization | [6 empty] | RF Parameter Optimization | Implementation solution for 2G Daily Maintenance and Cell Parameter Changes for PKG A | 2G | Completed |  | HW | 2023-10-01
140 | OSS Optimization | [6 empty] | Feature Implementation | Implementation Solution for Voice Quality Index Feature Enable in NPJHMBSC05 | 2G | Completed |  | HW | 2023-10-05
141 | OSS Optimization | [6 empty] | Feature Implementation | Implementation Solution for Voice Quality Index Feature Enable in ATRHMBSC04 | 2G | Completed |  | HW | 2023-10-05
142 | OSS Optimization | [6 empty] | Feature Implementation | Implementation Solution for Optimization of TBF Establishments Failure Due to No Channel | 2G | Completed |  | HW | 2023-10-06
143 | OSS Optimization | [6 empty] | RF Parameter Optimization | GSM Cell Optimization and RF Parameter Changes for daily maintenance. | 2G | Completed |  | HW | 2023-10-09
144 | OSS Optimization | [6 empty] | RF Parameter Optimization | 2G Cell Optimization and RF Parameter Changes for NTC Network Monthly | 2G | Completed |  | HW | 2023-10-18
145 | OSS Optimization | [6 empty] | RF Parameter Optimization | Cell Optimization and RF Parameter Changes for GSM Network-PKG B | 2G | Completed |  | HW | 2023-10-27
146 | OSS Optimization | [6 empty] | RF Parameter Optimization | Implementation solution for 3G Daily Maintenance and Cell Parameter Changes for PKG A and B | 2G | Completed |  | HW | 2023-11-03
147 | OSS Optimization | [6 empty] | RF Parameter Optimization | Optimization of TBF Establishments Failure Due to No Channel in CDR region | 2G | Completed |  | HW | 2023-11-03
148 | OSS Optimization | [6 empty] | RF Parameter Optimization | GSM Cell Optimization and RF Parameter Changes for daily maintenance. | 2G | Completed |  | HW | 2023-11-17
149 | OSS Optimization | [6 empty] | RF Parameter Optimization | Cell Optimization and RF Parameter Changes for NTC Network Monthly | 2G | Completed |  | HW | 2023-11-17
150 | OSS Optimization | [6 empty] | RF Parameter Optimization | Optimization of TBF Establishments Failure Due to No Channel in FWDR | 2G | Completed |  | HW | 2023-11-22
151 | OSS Optimization | [6 empty] | RF Parameter Optimization | Cell Optimization and RF Parameter Changes for GSM Network-PKG B | 2G | Completed |  | HW | 2023-12-01
152 | OSS Optimization | [6 empty] | RF Parameter Optimization | Implementation solution for 2G Daily Maintenance and Cell Parameter Changes for PKG A and B | 2G | Completed |  | HW | 2023-12-01
153 | OSS Optimization | [6 empty] | RF Parameter Optimization | Cell Optimization and RF Parameter Changes for NTC Network Monthly | 2G | Completed |  | HW | 2023-12-05
154 | OSS Optimization | [6 empty] | RF Parameter Optimization | Implementation solution for 3G Daily Maintenance and Cell Parameter Changes for PKG A and B | 3G | Completed |  | HW | 2023-12-25
155 | OSS Optimization | [6 empty] | RF Parameter Optimization | Cell Optimization and RF Parameter Changes for NTC Network Monthly | 2G | Completed |  | HW | 2024-01-01
156 | OSS Optimization | [6 empty] | RF Parameter Optimization | GSM Cell Optimization and RF Parameter Changes for daily maintenance january 2024 | 2G | Completed |  | HW | 2024-01-03
157 | OSS Optimization | [6 empty] | RF Parameter Optimization | Cell Optimization and RF Parameter Changes for GSM Network-PKG B | 2G | Completed |  | HW | 2024-01-05
158 | OSS Optimization | [6 empty] | RF Parameter Optimization | Implementation solution for 2G Daily Maintenance and Cell Parameter Changes for PKG A and B | 2G | Completed |  | HW | 2024-01-22
159 | OSS Optimization | [6 empty] | RF Parameter Optimization | NPS -GSM Cell Optimization and RF Parameter Changes for daily maintenance february 2024 | 2G | Completed |  | HW | 2024-01-31
160 | OSS Optimization | [6 empty] | RF Parameter Optimization | NPS 3G Cell Optimization and RF Parameter Changes Monthly | 3G | Completed |  | HW | 2024-02-01
161 | OSS Optimization | [6 empty] | RF Parameter Optimization | NPS - 2G Data Drop Optimization in EDR region | 2G | Completed |  | HW | 2024-02-02
162 | OSS Optimization | [6 empty] | RF Parameter Optimization | NPS - Implementation solution for 3G Daily Maintenance and Cell Parameter Changes for PKG A and B | 3G | Completed |  | HW | 2024-02-23
163 | OSS Optimization | [6 empty] | Neighbor Audit | NPS-2G Neighbor Audit, External Cell Definition and modification for BSC6900 Site Migration | 2G | Completed |  | HW | 2024-02-29
164 | OSS Optimization | [6 empty] | Neighbor Audit | NPS-3G Neighbor Audit, External Cell Definition and Parameter modification for BSC6910 migration | 3G | Completed |  | HW | 2024-03-01
165 | OSS Optimization | [6 empty] | RF Parameter Optimization | NPS -GSM Cell Optimization and RF Parameter Changes for daily maintenance march month 2024 | 2G | Completed |  | HW | 2024-03-01
166 | OSS Optimization | [6 empty] | RF Parameter Optimization | NPS-Cell Optimization and RF Parameter Changes for NTC Network Monthly | 2G | Completed |  | HW | 2024-03-01
167 | OSS Optimization | [6 empty] | RF Parameter Optimization | NPS-2g Automatic TRX Shutdown disable in Additional Sites | 2G | Completed |  | HW | 2024-03-13
168 | OSS Optimization | [6 empty] | Neighbor Audit | 2G Neighbor Audit Additional Site Package-A | 2G | Completed |  | HW | 2024-03-14
169 | OSS Optimization | [6 empty] | Neighbor Audit | NPS-2G Neighbor Audit Additional Site Package-B | 2G | Completed |  | HW | 2024-03-15
170 | OSS Optimization | [6 empty] | RF Parameter Optimization | NPS - Implementation Solution for 2G Data Drop Optimisation in TTCHBSC02. | 2G | Completed |  | HW | 2024-03-15
171 | OSS Optimization | [6 empty] | RF Parameter Optimization | NPS-3G Neighbor Audit, External Cell Definition and Parameter modification for BSC6910 migration | 3G | Completed |  | HW | 2024-03-22
172 | OSS Optimization | [6 empty] | RF Parameter Optimization | NPS - Implementation solution for 2G Daily Maintenance and Cell Parameter Changes for PKG A and B | 2G | Completed |  | HW | 2024-03-26
173 | OSS Optimization | [6 empty] | RF Parameter Optimization | NPS-Cell Optimization and RF Parameter Changes for NTC Network Monthly | 2G | Completed |  | HW | 2024-03-28
174 | OSS Optimization | [6 empty] | RF Parameter Optimization | NPS - GSM Cell Optimization and RF Parameter Changes for daily maintenance. | 2G | Completed |  | HW | 2024-04-01
175 | OSS Optimization | [6 empty] | Neighbor Audit | NPS-2G Neighbor Audit, External Cell Definition and modification for BSC6900 Site Migration | 2G | Completed |  | HW | 2024-04-05
176 | OSS Optimization | [6 empty] | RF Parameter Optimization | 2G Data Drop Optimization in KTM | 2G | Completed |  | HW | 2024-04-09
177 | OSS Optimization | [6 empty] | RF Parameter Optimization | Implementation solution for 2G Daily Maintenance and Cell Parameter Changes for PKG A and B | 2G | Completed |  | HW | 2024-04-17
178 | OSS Optimization | [6 empty] | RF Parameter Optimization | NPS - UMTS Cell Optimization and RF Parameter Changes for daily maintenance. | 3G | Completed |  | HW | 2024-04-19
179 | OSS Optimization | [6 empty] | RF Parameter Optimization | GSM Data Drop Optimization in BRTHMBSC11 of EDR Region | 2G | Completed |  | HW | 2024-04-19
180 | OSS Optimization | [6 empty] | Neighbor Audit | NPS-3G Neighbor Audit, External Cell Definition and Parameter modification for BSC6910 migration | 3G | Completed |  | HW | 2024-04-19
181 | OSS Optimization | [6 empty] | RF Parameter Optimization | NPS-Cell Optimization and RF Parameter Changes for NTC Network Monthly | 2G | Completed |  | HW | 2024-04-26
182 | OSS Optimization | [6 empty] | RF Parameter Optimization | NPS - GSM Cell Optimization and RF Parameter Changes for daily maintenance. | 2G | Completed |  | HW | 2024-04-29
183 | OSS Optimization | [6 empty] | RF Parameter Optimization | Optimization of Uplink and Downlink Power congestion of Package-A Network | 2G | Completed |  | HW | 2024-05-03
184 | Network RF Complain | KTM | Kyonjosym Municipality Lalitpur |  | Kyonjosym Municipality Lalitpur | 27.5482 | 85.4007 | RF Parameter Optimization | TRX Power increament 2G 3G | 2G 3G | Completed |  | NT | 2024-05-20 | The main serving site was KTM254_Phulchowki. After power increment the signal strenght changed from -75 to upto -65. The traffice was huge on the Jestha 10. The change in traffic was from 1 erlang to 31 erlang.
185 | Network RF Complain | CDR | Timure Rashuwagadhi |  | Rasuwagadhi | 28.2553 | 85.3669 | Sector Expansion Survey | Sector Expansion | 2G 3G | Completed |  | HW | 2024-05-22
186 | Network RF Complain | KTM | Beshi Gaun Laligurash Tole Customer Complain |  | Beshi Gaun Laligurash Tole Customer Complain | 27.7298 | 85.3821 | Drive Test & Optimization | Azimuth of KTM233_NepalMedicalCollege-B changed from 95 to 120 | 2G 3G | Completed |  | HW | 2024-04-10 | Recommeded to Add 2G in the existing KTM853_MAKALBARI.
187 | Network RF Complain | KTM | Gothatar Khadaghari Complain |  | Gothatar Khadaghari Complain | 27.7018 | 85.3782 | Drive Test & Optimization | Electrical Tilt of KTM172_Khadkagaon_C changed from 6 to 3 >Electrical Tilt of KTM605_ForceParkBusstop_R changed from 5 to 2 | 2G 3G | Completed |  | HW | 2024-04-08 | Recommeded to Add 2G in the existing KTM759_GothatarArea .
188 | Network RF Complain | KTM | Grihini Foods Udhyog Customer Complain |  | Grihini Foods Udhyog Customer Complain | 27.6967 | 85.3519 | Drive Test & Optimization | >Electrical Tilt and azimuth of KTM172_Khadkagaon_C changed from 2 to 1 and from 145 to 155 >Azimuth of KTM290_SitaAirOmnagar-Q changed from 150 to 160 | 2G 3G | Completed |  | HW | 2024-04-03 | Satisfactory
189 | Network RF Complain | KTM | HAMRO COLONY CUSTOMER COMPLAIN |  | HAMRO COLONY CUSTOMER COMPLAIN | 27.6604 | 85.3375 | Drive Test & Optimization | >Mechanical Tilt and azimuth of KTM910_Bodhigram2-C changed from 3 to 2 and from 250 to 260 >Mechanical Tilt and Electrical Tilt of KTM365_KrishnaMandirImadol-R changed from 4 to 2 and 3 to 2 | 2G 3G | Completed |  | HW | 2024-04-14 | Recommeded to Add 2G/3G in the existing KTM680_Bodhigram .
190 | Network RF Complain | KTM | KAMEROTAR AREA CUSTOMER COMPLAIN |  | KAMEROTAR AREA CUSTOMER COMPLAIN | 27.678 | 85.393 | Drive Test & Optimization | >Mechanical Tilt and azimuth of Ktm026_Sichuhani-B/E changed from 8 to 2 and 115 to 100 >Mechanical Tilt of Ktm026_Sichuhani-Q from 2 to 0 >Electrical Tilt of Ktm670_Tahanani-Q from 3 to 2 | 2G 3G | Completed |  | HW | 2024-04-14 | Recommeded to Add 2G/3G in the existing KTM571 .
191 | Network RF Complain | KTM | NABIL BANK CUSTOMER COMPLAIN |  | NABIL BANK CUSTOMER COMPLAIN | 27.6698 | 85.4098 | Drive Test & Optimization | >Mechanical Tilt and Electrical Tilt of KTM035_Sallaghari-B changed from 1 to 2 and 2 to 4 >Mechanical Tilt and azimuth of KTM035_Sallaghari-Q changed from 1 to 2 and from 105 to 120 | 2G 3G | Completed |  | HW | 2024-04-11 | Recommeded to Add Small Cell inside the building .
192 | Network RF Complain | KTM | NEAR SUMMIT HOTEL CUSTOMER COMPLAIN |  | NEAR SUMMIT HOTEL CUSTOMER COMPLAIN | 27.6857 | 85.3125 | Drive Test & Optimization | >Network Coveage and quality seems good | 2G 3G | Completed |  | HW | 2024-04-11 | Solved
193 | Network RF Complain | KTM | PIPALBOT NEWROAD CUSTOMER COMPLAIN |  | PIPALBOT NEWROAD CUSTOMER COMPLAIN | 27.7032 | 85.3104 | Drive Test & Optimization | >Electrical Tilt of KTM099_CrystalHotel-B changed from 5 to 3 >Mecanical Tilt of KTM099_CrystalHotel-Q changed from 1 to 2 | 2G 3G | Completed |  | HW | 2024-04-15 | Solved
194 | Network RF Complain | KTM | Sagarmatha Pipal Tole Custumer Complain |  | Sagarmatha Pipal Tole Custumer Complain | 27.744 | 85.3862 | Drive Test & Optimization | >Electrical Tilt of KTM168_KapanPhulbari_B changed from 5 to 3 >Electrical Tilt of KTM168_KapanPhulbari_Q changed from 10 to 6 >Pilot Power of KTM129_Gokarneswor_P changed from 33dbm to 34dbm | 2G 3G | Completed |  | HW | 2024-04-02 | Satisfactory
195 | Network RF Complain | KTM | SICHUAN HOTEL CUSTOMER COMPLAIN |  | SICHUAN HOTEL CUSTOMER COMPLAIN | 27.7114 | 85.3142 | Drive Test & Optimization | >Azimuth of KTM233_NepalMedicalCollege-B changed from 290 to 300 >Electrical Tilt, Mechanical Tilt and azimuth of KTM165_Kantipath-R changed from 3 to 2, 1 to 2 and 255 to 275 | 2G 3G | Completed |  | HW | 2024-04-10 | Recommeded to maintain IBS installed inside the building .
196 | Network RF Complain | KTM | Silauto Resort Areas Customer Complain |  | Silauto Resort Areas Customer Complain | 27.716 | 85.2297 | Drive Test & Optimization | >Azimuth of KTM146_G_Indrasthan Expansion changed from 25 to 15 | 2G 3G | Completed |  | HW | 2024-04-15 | Solved
197 | Network RF Complain | KTM | Siphal Customer Complain |  | Siphal Customer Complain | 27.7132 | 85.34 | Drive Test & Optimization | >Electrical Tilt, Mechanical Tilt and azimuth of KTM633_Sano_Gaucharan_B changed from 4 to 2, 3 to 0 and 125 to 110 >Electrical Tilt, Mechanical Tilt and azimuth of KTM633_Sano_Gaucharan_Q changed from 3 to 2, 2 to 1 and 130 to 110 | 2G 3G | Completed |  | HW | 2024-04-08 | Recommended to add new site at lat/long: : 27.713065°/ 85.341271 .
198 | Network RF Complain | KTM | SS Chowk Customer Complain |  | SS Chowk Customer Complain | 27.6721 | 85.3904 | Drive Test & Optimization | >Mechanical Tilt and azimuth of KTM043_THIMI-A changed from 3 to 2 and 75 to 110 >Mechanical Tilt and azimuth of KTM043_THIMI-C changed from 5 to 3 and 330 to 0 >Mechanical Tilt and azimuth of KTM043_THIMI-C changed from 5 to 3 and 340 to 10 | 2G 3G | Completed |  | HW | 2024-04-12 | Satisfactory
199 | Network RF Complain | KTM | SundarBasti Customer Complain |  | SundarBasti Customer Complain | 27.7499 | 85.3545 | Drive Test & Optimization | >Electrical Tilt of KTM166_KapanLasumtar-C changed from 8 to 2 >Electrical Tilt and azimuth of KTM166_KapanLasumtar-P changed from 6 to 3 and 325 to 305 | 2G 3G | Completed |  | HW | 2024-04-18 | Recommended to add new site at Lat: 27.750179° Long: 85.354934°. .
200 | Network RF Complain | KTM | Gokarna Ward 9 Customer Complain |  | Gokarna Ward 9 Customer Complain | 27.7366 | 85.3752 | Drive Test & Optimization | >Electrical Tilt and Azimuth of KTM168_KapanPhulbari –B changed from 5 to 3 and 130 to 120 >Electrical Tilt and Azimuth of KTM168_KapanPhulbari –Q changed from 10 to 6 and 120 to 110 | 2G 3G | Completed |  | HW | 2024-05-09 | Recommended to add new site at lat/long: : 27.732965°/ 85.376980° . Recommeded to Add 2G/3G in the existing KTM830_Gokarna_Height
201 | Network RF Complain | KTM | Himali Marg Customer Complain |  | Himali Marg Customer Complain | 27.6799 | 85.3465 | Drive Test & Optimization | >Electrical Tilt of KTM180_Koteshwor-C changed from 3 to 2 >Electrical Tilt of KTM180_Koteshwor-R changed from 5 to 3 | 2G 3G | Completed |  | HW | 2024-05-02 | Recommeded to Add 2G/3G in the existing KTM897_Koteshwor_chowk .
202 | Network RF Complain | KTM | B.G. Fiber Play Bhangal Kapan Customer Complain |  | B.G. Fiber Play Bhangal Kapan Customer Complain | 27.7545 | 85.3558 | Drive Test & Optimization | >Electrical Tilt and azimuth of KTM652_BHANGAL¬_Q changed from 0 to 2 and from 190 to 210 | 2G 3G | Completed |  | HW | 2024-05-06 | Recommeded to Add 2G/3G in the existing KTM556_TALLO_BHANGAL .
203 | Network RF Complain | KTM | GIBSON NIBAS CUSTOMER COMPLAIN |  | GIBSON NIBAS CUSTOMER COMPLAIN | 27.7237 | 85.4035 | Drive Test & Optimization | >Electrical Tilt and Azimuth of KTM306_Thali-B/E changed from 5/6 to 2/3 and 210 to 220 >Azimuth of KTM306_Thali-P changed from 50 to 10 >Mechanical Tilt and Electrical Tilt of KTM306_Thali-R changed from 3 to 5 and 5 to 3 | 2G 3G | Completed |  | HW | 2024-05-05 | Recommeded sector expansion of KTM306_Thali on Lat: 27.723701° Long: 85.402649°.
204 | Network RF Complain | KTM | GONGABHU CUSTOMER COMPLAIN |  | GONGABHU CUSTOMER COMPLAIN | 27.7357 | 85.3143 | Drive Test & Optimization | >Electrical Tilt and azimuth of KTM133_Gongabu2-B changed from 5 to 3 and 125 to 105 >Pilot Power of KTM132_Laxmi_Guest_House_Expansion_S1 changed from 330dbm to 345dbm | 2G 3G | Completed |  | HW | 2024-05-02 | Satisfactory
205 | Network RF Complain | KTM | GREEN VALLEY APARTMENT Customer Complain |  | GREEN VALLEY APARTMENT Customer Complain | 27.6275 | 85.3869 | Drive Test & Optimization | >Pilot Power of KTM369_Lamatar1 -R changed from 330dbm to 345dbm | 2G 3G | Completed |  | HW | 2024-05-02 | Recommeded extended sector from KTM369_Lamatar1 at lat/long( 27.627376°/ 85.386476°). .
206 | Network RF Complain | KTM | Imadol Near Udayapure Fresh House Customer Complain |  | Imadol Near Udayapure Fresh House Customer Complain | 27.6608 | 85.352 | Drive Test & Optimization | >Electrical Tilt of KTM385_SanogounLubhu-A changed from 0 to 1 >Mecanical Tilt of KTM360_Imadol -P changed from 1 to 2 | 2G 3G | Completed |  | HW | 2023-05-05 | Solved
207 | Network RF Complain | KTM | Dhammagara Vipassana Meditation Centre Customer Complain |  | Dhammagara Vipassana Meditation Centre Customer Complain | 27.6191 | 85.3898 | Drive Test & Optimization | >Electrical Tilt of KTM349_Godamchaur-Q changed from 3 to 2 | 2G 3G | Completed |  | HW | 2024-05-07 | Recommended to add new site at lat/long: 27.618723°/85.389898°.
208 | Network RF Complain | KTM | MANMOHAN BUILDING TEACHING HOSPITAL CUSTOMERS COMPLAIN |  | MANMOHAN BUILDING TEACHING HOSPITAL CUSTOMERS COMPLAIN | 27.7357 | 85.3287 | Drive Test & Optimization | >Electrical Tilt and Mechanical Tilt of KTM200_Maharajgunj_C changed from 4 to 3 and 3 to 5 >Electrical Tilt and Mechanical Tilt of KTM200_Maharajgunj_C changed from 5 to 4 and 3 to 5 | 2G 3G | Completed |  | HW | 2024-05-08 | Relocation of Book RRU and Add 2G in Book RRU
209 | Network RF Complain | KTM | NEPAL APF SCHOOL CUSTOMER COMPLAIN |  | NEPAL APF SCHOOL CUSTOMER COMPLAIN | 27.6609 | 85.2562 | Drive Test & Optimization | >Network Coveage and quality seems good | 2G 3G | Completed |  | HW | 2024-05-10 | Solved
210 | Network RF Complain | KTM | NT OFFICE CUSTOMER COMPLAIN |  | NT OFFICE CUSTOMER COMPLAIN | 27.6724 | 85.3134 | Drive Test & Optimization | >Network Coveage and quality seems good except ehere IBS was not working | 2G 3G | Completed |  | HW | 2024-05-06 | Recommeded to maintain IBS installed inside the building .
211 | Network RF Complain | KTM | OCHU HEIGHT CUSTOMER COMPLAIN |  | OCHU HEIGHT CUSTOMER COMPLAIN | 27.6501 | 85.3437 | Drive Test & Optimization | >Electrical Tilt and azimuth of KTM391_Sitapakha-A changed from 5 to 2 and 30 to 40 >Electrical Tilt and azimuth of KTM391_Sitapakha-P changed from 3 to 2 and 40 to 50 | 2G 3G | Completed |  | HW | 2024-05-12 | Recommended to add new site at lat/long: : 27.650148° / 85.347010°.
212 | Network RF Complain | KTM | RANIGHATA CHOWK CUSTOMER COMPLAIN |  | RANIGHATA CHOWK CUSTOMER COMPLAIN | 27.7144 | 85.2763 | Drive Test & Optimization | >Azimuth of KTM302_Swoyambhu-C changed from 240mt0 250 >Electrical Tilt and azimuth of KTM616_Sharanpur-Q changed from 3 to 2 and 110 to 100 | 2G 3G | Completed |  | HW | 2024-05-03 | Satisfactory
213 | Network RF Complain | KTM | Rapalta Cottage Complain |  | Rapalta Cottage Complain | 27.7703 | 85.3823 | Drive Test & Optimization | >No Changes was made because of lack of sites | 2G 3G | Completed |  | HW | 2024-05-06 | Recommended to add 2G/3G sector atKTM443_Tarebhir_Micro Recommeded to Add Small Cell lat/long: 27.728344°/85.345118°.
214 | Network RF Complain | KTM | Thapagaun Area Customer Complain |  | Thapagaun Area Customer Complain | 27.6901 | 85.3302 | Drive Test & Optimization | >Mechanical Tilt and Azimuth of KTM708_Krishna_Tower_Micro_B changed from 2 to 1 and 60 to 70 >Mechanical Tilt and Azimuth of KTM311_ThpaGaun_A changed from 2 to 1 and 20 to 30 >Azimuth of KTM708_Krishna_Tower_Micro_Q changed from 60 TO 50 >Azimuth of KTM311_ThpaGaun_P changed from 20 TO 30 | 2G 3G | Completed |  | HW | 2024-05-06 | Recommended to add 2G sector at KTM708_Krishna_Tower_Micro Recommeded to Add 2G/3G sector at the existing KTM311_ThpaGaun Recommended to add 2G (900MHz) at KTM708_Krishna_Tower_Micro
215 | Network RF Complain | KTM | Tikathali Sarkidil Customer Complain |  | Tikathali Sarkidil Customer Complain | 27.6614 | 85.3565 | Drive Test & Optimization | >Azimuth of KTM360_Imadol -B changed from 130 to 100 >Electrical Tilt of KTM603_Tikathali2-P changed from 3 to 2 | 2G 3G | Completed |  | HW | 2024-05-13 | Recommeded to Add 2G in the existing KTM603_Tikathali2 .
216 | Network Coverage Expansion | KTM | Budhanilkantha Municipality | KTM744_Chunikhel | Budhanilkantha Municipality | 27.7622 | 85.3772 | 2G Addition | To address customer complai and improve 2G Coverage in Budhanilkantha Area 2G is added on 4G only site KTM744 | 2G | Completed |  |  | 2024-05-13
217 | Network Coverage Expansion | KTM | Hattiban | KTM850_DHAPAKHEL APARTMENT_3G | Hattiban | 27.6426 | 85.3284 | 2G Addition | To address customer complain and improve 2G Coverage inHattiban Area Area 2G is added on 3G/4G only site KTM850 |  | Completed |  |  | 2024-05-13
218 | Network Coverage Expansion | KTM | BhagwanbahaThamel | BhagwanbahaThamel | Bhagwanbahal and sanchaykos areaThamel | 27.715 | 85.3127 | 2G Addition | To address customer complain and improve 2G Coverage in Bhagwanbahal and IRD office Thamel Area 2G is added on 4G only site |  | Completed |  |  | 2024-05-13
219 | OSS Optimization | KTM | [5 empty] | Feature Implementation | Implementation solution for 2G Daily Maintenance and Cell Parameter Changes for PKG A and B |  | Completed |  | HW | 2024-06-07 11:53
220 | OSS Optimization | KTM | [5 empty] | RF Parameter Optimization | NPS - UMTS Cell Optimization and RF Parameter Changes for daily maintenance. |  | Completed |  | HW | 2024-05-17 10:47
221 | OSS Optimization | KTM | [5 empty] | Feature Implementation | Implementation solution for 3G Daily Maintenance and Cell Parameter Changes for PKG A and B |  | Completed |  | HW | 2024-05-17 09:32
222 | OSS Optimization | KTM | [5 empty] | RF Parameter Optimization | NPS-GSM Cell Optimization and RF Parameter Changes for daily maintenance. |  | Completed |  | HW | 2024-05-27 14:50
223 | OSS Optimization | KTM | [5 empty] | RF Parameter Optimization | NPS-Cell Optimization and RF Parameter Changes for NTC Network Monthly |  | Completed |  | HW | 2024-05-24 14:38
224 | Network RF Complain | KTM | Office of Auditor General Kalikasthan |  | Office of Auditor General Kalikasthan | 27.6974 | 85.3219 | Drive Test & Optimization | Indoor coverage issue complain from customer of Office of Auditor General | 2G 3G 4G | Completed |  | NT | 2024-05-21
225 | Network Expansion | KTM | Pabitra Nagar Kathmandu | KTM755_GONGABU PABITRANAGAR | House Owner Complain | 27.7305 | 85.3128 | Site Survey | Existing site relocation as per owner request and new house around 200m was surveyed for the RTT | 2G 3G 4G | Planned |  | NT | 2024-06-06 | Existing site relocation as per owner request and new house around 200m was surveyed for the RTT
226 | Network Expansion | KTM | NABIL BANK CUSTOMER COMPLAIN |  | Nabil Bank Shallaghari Bhaktapur | 27.67 | 85.4102 | Site Survey | Survey for small cell installation | 3G 4G | Planned |  | NT | 2024-05-26
227 | Others | KTM | Chochhe Bhaktapur |  | Chochhe Bhaktapur |  |  | Repeater Dismantled | Repeater dismantled |  | Planned |  |  | 2024-05-15
228 | Network Expansion | KTM | Ranjana Trade Mall | KTM099_CrystalHotel | Ranjana Trade Mall | 27.7045 | 85.3103 | Sector Expansion | Sector Expansion with indoor dash in Ranjana Trade Mall | 3G | Completed |  |  | 2024-05-30
229 | Network Expansion | KTM | Nagdhunga Tunnel |  | Nagdhunga Tunnel | 27.7022 | 85.2236 | Site Survey | Site and Sector Survey for nagdhunga indoor and tunnel | 2G 3G 4G | Planned |  |  | 2024-05-16
230 | Network Expansion | KTM | CG Hotel Sanepa |  | CG Hotel Sanepa | 27.6786 | 85.313 | Site Survey | Site Survey for indoor solution | 3G | Planned |  |  | 2024-05-08